## Summary Dashboard
Pithy Backend & Frontend — Full Task Log
Spring Boot Security Audit · Feature Additions · Bug Fixes ¦ Session: March 2026
BUG FIXES |  | FEATURE ADDITIONS |  | SECURITY AUDIT
2 |  | 4 |  | 30 found
Resolved DB constraint & Hibernate JSON binding issues |  | Admin results pages, sidebar dropdowns, API proxy routes |  | 7 Critical · 9 High · 10 Medium · 4 Low identified
Security Fixes — Breakdown by Severity
CRITICAL | HIGH |  | MEDIUM | LOW | TOTAL
7 Fixed | 9 Fixed |  | 10 Fixed | 4 Documented | 30 Items

## All Tasks
# | Date | Category | Priority | Task Title | Description | Files Modified | Status
1 | 25 Mar 2026 | Bug Fix | Medium | Fix likert_response NOT NULL constraint | Hibernate INSERT no longer included likert_response column after entity refactor, but DB still enforced NOT NULL. Fixed by running ALTER TABLE assessment_responses ALTER COLUMN likert_response DROP NOT NULL. | DB migration SQL (manual) | ✅ Done
2 | 25 Mar 2026 | Bug Fix | High | Fix dimension_percentages jsonb type mismatch | @Column(columnDefinition='jsonb') only affects DDL, not runtime binding. Added @JdbcTypeCode(SqlTypes.JSON) annotation on dimensionScores and dimensionPercentages fields in PersonalityResult entity so Hibernate 6 binds them as JSON at runtime, not varchar. | Entity/PersonalityResult.java | ✅ Done
3 | 26 Mar 2026 | Feature | Medium | Add admin scenario assessment results page | Violet-themed results page with stats strip, personality type distribution, search/filter, and sortable table. Displays all scenario assessments across all users. | app/human-services/admin/scenario-assessments/page.tsx | ✅ Done
4 | 26 Mar 2026 | Feature | Medium | Add GET /api/admin/scenario-assessments endpoint | Backend endpoint returning all scenario assessments enriched with user email, response count, and personality type. Added AdminScenarioAssessmentResultDTO record and corresponding AdminService + AdminController methods. | AdminController.java, AdminService.java, AssessmentDTOs.java, ScenarioResponseRepository.java | ✅ Done
5 | 26 Mar 2026 | Feature | Low | Add collapsible AdminSidebar dropdown groups | Replaced flat links array with NavItem union type (SimpleLink ¦ DropdownGroup). Two collapsible groups: 'Manage Assessment' (Questions + Results) and 'Manage Scenario Assessment' (Questions + Scenario Results). Auto-opens group containing current path. Collapses to icons when sidebar is collapsed. | components/AdminSidebar.tsx | ✅ Done
6 | 26 Mar 2026 | Bug Fix | High | Fix 'Failed to load scenario assessment results' | Frontend called /api/admin/scenario-assessments but no Next.js API route existed to proxy the request to the Spring Boot backend. Created the missing proxy route that reads auth token from cookies and forwards to backend. | app/api/admin/scenario-assessments/route.ts | ✅ Done
7 | 27 Mar 2026 | Security – Critical | Critical | Fix IDOR on ProfileController | Profile endpoints (POST, PUT, DELETE) accepted any userId without verifying the caller owned the profile. Added @AuthenticationPrincipal CustomUserDetails and ownership check via profileRepository.findByUserId(). Returns 403 for mismatches. Removed all System.out.println / e.printStackTrace() debug leaks. | Controller/ProfileController.java | ✅ Done
8 | 27 Mar 2026 | Security – Critical | Critical | Fix IDOR on PostController | Create, update, and delete post endpoints accepted a userId request param allowing any user to post/modify as another user. Replaced @RequestParam userId with @AuthenticationPrincipal so userId is always derived from the JWT. | Controller/PostController.java | ✅ Done
9 | 27 Mar 2026 | Security – Critical | Critical | Fix IDOR on CommentController | Comment mutation endpoints accepted profileId in the request body, allowing callers to post/edit/delete as any profile. Injected ProfileRepository and added resolveProfileId() helper that derives profileId from the authenticated JWT. | Controller/CommentController.java | ✅ Done
10 | 27 Mar 2026 | Security – Critical | Critical | Implement JWT tokenVersion invalidation on logout | Added tokenVersion int field on User entity and incrementTokenVersion() helper. JwtAuthenticationFilter now extracts tokenVersion claim and compares to DB value; tokens issued before logout are immediately rejected. Added POST /api/users/logout endpoint that increments version and clears currentToken. | Entity/User.java, Config/JwtAuthenticationFilter.java, Service/JwtService.java, Service/UserService.java, Controller/UserController.java | ✅ Done
11 | 27 Mar 2026 | Security – Critical | Critical | File upload magic byte validation | FileUploadService previously trusted only Content-Type headers which can be spoofed. Added magic byte maps for images (JPEG FF D8 FF, PNG 89 50 4E 47, GIF, WebP) and videos (MP4, MPEG, WebM, AVI). validateImage() / validateVideo() read first 12 bytes and reject mismatches before storage. | Service/FileUploadService.java | ✅ Done
12 | 27 Mar 2026 | Security – Critical | Critical | Fix path traversal in file deletion | deleteFile() did not sanitise caller-supplied filenames. Added toAbsolutePath().normalize() and an assertion that the resolved path starts with the configured upload root directory. uploadFile() also strips path separators from filenames and uses UUID-only storage names. | Service/FileUploadService.java | ✅ Done
13 | 27 Mar 2026 | Security – Critical | Critical | Flutterwave webhook signature validation | Webhook endpoint accepted and processed any incoming request without verifying authenticity. Added verif-hash header validation against the Flutterwave secret key using timing-safe MessageDigest.isEqual(). Also validated payment redirect URLs against configured frontend domain. | Controller/PaymentController.java, Service/FlutterwavePaymentService.java | ✅ Done
14 | 28 Mar 2026 | Security – High | High | Remove debug leaks from JwtAuthenticationFilter | Filter contained numerous System.out.println calls that leaked JWT contents, user emails, and token validation details to stdout. Replaced all with SLF4J logger at appropriate levels (debug/warn/error). | Config/JwtAuthenticationFilter.java | ✅ Done
15 | 28 Mar 2026 | Security – High | High | Restrict CORS to explicit origins | SecurityConfig had setAllowedOriginPatterns(List.of('*')) allowing any origin. Injected app.frontend-url and app.base-url properties and changed to setAllowedOrigins(List.of(frontendUrl, baseUrl)). Restricted allowed headers to Authorization, Content-Type, Accept only. | Config/SecurityConfig.java | ✅ Done
16 | 28 Mar 2026 | Security – High | High | Restrict WebSocket CORS origins | WebSocketConfig used setAllowedOriginPatterns('*'). Injected app.frontend-url property and changed to setAllowedOrigins(frontendUrl). | Config/WebSocketConfig.java | ✅ Done
17 | 28 Mar 2026 | Security – High | High | Add tokenVersion claim to JWT generation | JwtService.generateToken() did not include tokenVersion in the token. Added claim extraction from CustomUserDetails.getUser().getTokenVersion() and new extractTokenVersion() method returning int (-1 if absent). | Service/JwtService.java | ✅ Done
18 | 28 Mar 2026 | Security – High | High | Add ownership checks to UserController | PUT /{id}, PUT /{id}/change-password, and DELETE /{id} did not verify the caller was the target user. Added @AuthenticationPrincipal and IDOR checks returning 403 for mismatches. Added ADMIN-only restriction to GET /email/{email}. Generic error messages replacing raw exception messages. | Controller/UserController.java | ✅ Done
19 | 28 Mar 2026 | Security – High | High | Validate Flutterwave payment redirect URL | initiatePayment() accepted an arbitrary caller-supplied redirect URL enabling open redirect attacks. Added validateRedirectUrl() that parses the URI and asserts the host matches the configured frontend domain. | Service/FlutterwavePaymentService.java | ✅ Done
20 | 28 Mar 2026 | Security – High | High | Rate limiting for forgot-password endpoint | No rate limit existed on /api/users/forgot-password allowing unlimited password reset email spam. Added 3-request-per-hour-per-IP limit via RateLimitFilter and RateLimitService using Redis. | Config/RateLimitFilter.java, Service/RateLimitService.java | ✅ Done
21 | 28 Mar 2026 | Security – High | High | Rate limiting for resend-verification endpoint | No rate limit on /api/users/resend-verification. Added 3-request-per-hour-per-IP limit consistent with forgot-password protection. | Config/RateLimitFilter.java, Service/RateLimitService.java | ✅ Done
22 | 28 Mar 2026 | Security – High | High | Trusted proxy X-Forwarded-For handling | getClientIP() unconditionally trusted the X-Forwarded-For header, allowing IP spoofing to bypass rate limiting. Added app.trusted-proxies config and isTrustedProxy() check — XFF only used when the direct connection IP is a configured trusted proxy. | Config/RateLimitFilter.java, resources/application.properties | ✅ Done
23 | 29 Mar 2026 | Security – Medium | Medium | Rate limiting for reset-password endpoint | Added 5-request-per-hour-per-IP limit for /api/users/reset-password. Added RESET_PWD_LIMIT=5, RESET_PWD_WINDOW_SECONDS=3600, checkResetPasswordLimit() in RateLimitService and corresponding filter handler. | Config/RateLimitFilter.java, Service/RateLimitService.java | ✅ Done
24 | 29 Mar 2026 | Security – Medium | Medium | Rate limiting for change-password endpoint | Added 5-request-per-hour-per-IP limit for /api/users/{id}/change-password. Added CHANGE_PWD_LIMIT=5 constant, checkChangePasswordLimit() and wired into RateLimitFilter for paths matching /change-password suffix. | Config/RateLimitFilter.java, Service/RateLimitService.java | ✅ Done
25 | 29 Mar 2026 | Security – Medium | Medium | Timing-safe token comparison for email verification | verifyEmail() used DB lookup as implicit comparison but lacked explicit constant-time comparison. Added timingSafeEquals() using MessageDigest.isEqual() and applied it after the DB lookup to prevent timing oracle attacks. | Service/UserService.java | ✅ Done
26 | 29 Mar 2026 | Security – Medium | Medium | Timing-safe token comparison for password reset | resetPassword() had same timing oracle risk as verifyEmail(). Applied timingSafeEquals(token, user.getResetToken()) before processing the reset, using the same MessageDigest.isEqual() helper. | Service/UserService.java | ✅ Done
27 | 29 Mar 2026 | Security – Medium | Medium | Add ADMIN-only auth to job applications endpoint | GET /api/applications/jobs/{jobId} (admin/employer view of all applications) had no authorization check — any authenticated user could access it. Added @PreAuthorize("hasAuthority('ADMIN')") annotation. | Controller/JobApplicationController.java | ✅ Done
28 | 30 Mar 2026 | Security – Medium | Medium | Paginate admin/users endpoint | GET /api/admin/users called userRepository.findAll() with no limit, risking OOM on large datasets. Added page/size request params (default 50, capped 100), PageRequest.of() in controller, and Pageable parameter in AdminService. Updated frontend getAdminUsers() action to handle Spring Page<> response. | Controller/AdminController.java, Service/AdminService.java, lib/actions/admin.actions.ts | ✅ Done
29 | 30 Mar 2026 | Security – Medium | Medium | Paginate admin payments endpoints | GET /api/admin/payments and /api/admin/payments/scenario returned unbounded lists. Both paginated to max 100 per page. Frontend payment actions updated to extract .content from Spring Page<> responses. | Controller/AdminController.java, Service/AdminService.java, lib/actions/payment.actions.ts | ✅ Done
30 | 30 Mar 2026 | Security – Medium | Medium | Paginate admin assessments and scenario-assessments endpoints | GET /api/admin/assessments and /api/admin/scenario-assessments returned full unbounded lists. Both paginated. Frontend admin result pages updated from setRows(data) to setRows(data.content ?? []). | Controller/AdminController.java, Service/AdminService.java, app/human-services/admin/assessments/page.tsx, app/human-services/admin/scenario-assessments/page.tsx | ✅ Done
31 | 30 Mar 2026 | Security – Medium | Medium | Replace all System.err/out.println with SLF4J | Remaining debug prints in UserService (registration, email verification), JobScheduler, GeoLocationService, and FundingViewService replaced with SLF4J log.info / log.warn / log.error calls. Zero debug prints remain in codebase. | Service/UserService.java, Schedule/JobScheduler.java, Service/GeoLocationService.java, Service/FundingViewService.java | ✅ Done
32 | 31 Mar 2026 | Test Fix | Medium | Fix AdminServiceTest – getAllUserSummaries() Pageable arg | Pagination refactor changed getAllUserSummaries() signature to require Pageable. Updated two test cases: stubs changed from userRepository.findAll() returning List to userRepository.findAll(any(Pageable.class)) returning PageImpl<>. Assertions updated to use .getContent(). | test/.../Service/AdminServiceTest.java | ✅ Done
33 | 31 Mar 2026 | Test Fix | Medium | Fix AdminServiceTest – getAllCoursePayments() Pageable arg | Pagination refactor changed getAllCoursePayments() signature to require Pageable. Updated test stub from paymentRepository.findAll() to paymentRepository.findAll(any(Pageable.class)) returning PageImpl<>(List.of()). Assertion updated to .getContent().isEmpty(). Added Spring Data Pageable imports and removed unused Enrollment import. | test/.../Service/AdminServiceTest.java | ✅ Done

## Security Audit Register
# | Vulnerability Type | Severity | Description & Attack Vector | Fix Applied | Status
1 | IDOR | Critical | ProfileController POST/PUT/DELETE accepted any userId — attacker could create/edit/delete other users' profiles | Added @AuthenticationPrincipal + ownership check via profileRepository.findByUserId() | ✅ Fixed
2 | IDOR | Critical | PostController create/update/delete accepted userId request param — attacker could post as any user | Replaced @RequestParam userId with JWT-derived currentUser.getUser().getId() | ✅ Fixed
3 | IDOR | Critical | CommentController accepted profileId in request body — attacker could comment/edit/delete as any profile | Added resolveProfileId() helper deriving profileId from authenticated JWT | ✅ Fixed
4 | Broken Auth – Logout | Critical | No server-side JWT invalidation on logout — stolen tokens remain valid indefinitely after logout | Added tokenVersion field on User; filter rejects tokens with stale version; logout increments version | ✅ Fixed
5 | Unrestricted Upload | Critical | File uploads validated only Content-Type header (easily spoofed) — allowed uploading malicious files as images/videos | Added magic byte validation reading first 12 bytes for JPEG, PNG, GIF, WebP, MP4, WebM, AVI, MPEG | ✅ Fixed
6 | Path Traversal | Critical | deleteFile() accepted raw filename from caller — attacker could delete arbitrary files outside upload directory | Added normalize() + prefix assertion; uploadFile() uses UUID-only filenames stripping path separators | ✅ Fixed
7 | Webhook Forgery | Critical | Flutterwave webhook endpoint processed any incoming POST without verifying verif-hash signature | Added timing-safe verif-hash validation using MessageDigest.isEqual() before processing | ✅ Fixed
8 | Information Leakage | High | JwtAuthenticationFilter had System.out.println calls leaking JWT contents and user emails to stdout/logs | Replaced all with SLF4J logger at appropriate debug/warn/error levels | ✅ Fixed
9 | Overly Broad CORS | High | CORS config used setAllowedOriginPatterns('*') — any origin could make credentialed cross-origin requests | Changed to explicit setAllowedOrigins(List.of(frontendUrl, baseUrl)) with restricted headers | ✅ Fixed
10 | Overly Broad WS CORS | High | WebSocket CORS used setAllowedOriginPatterns('*') — any origin could establish WebSocket connections | Injected app.frontend-url and changed to setAllowedOrigins(frontendUrl) | ✅ Fixed
11 | JWT – Missing Claim | High | JWT tokens did not include tokenVersion claim — cannot detect revoked tokens server-side | generateToken() now embeds tokenVersion claim; extractTokenVersion() parses it from incoming tokens | ✅ Fixed
12 | IDOR – User Account | High | PUT /{id} and DELETE /{id} in UserController had no ownership check — attacker could modify/delete any account | Added @AuthenticationPrincipal and IDOR checks; 403 returned for cross-user attempts | ✅ Fixed
13 | Open Redirect | High | initiatePayment() accepted arbitrary caller-supplied redirect URL enabling phishing via open redirect | Added validateRedirectUrl() parsing URI and asserting host matches configured frontend domain | ✅ Fixed
14 | No Rate Limit – ForgotPwd | High | /api/users/forgot-password had no rate limiting — could spam users with reset emails | Added 3 req/hr/IP limit via RateLimitFilter + RateLimitService (Redis-backed) | ✅ Fixed
15 | No Rate Limit – ResendVer | High | /api/users/resend-verification had no rate limiting — could spam verification emails | Added 3 req/hr/IP limit consistent with forgot-password protection | ✅ Fixed
16 | IP Spoofing – XFF | High | getClientIP() unconditionally trusted X-Forwarded-For — attacker could spoof IP to bypass rate limits | Added trusted-proxies config; XFF only trusted when direct connection comes from a configured trusted proxy | ✅ Fixed
17 | No Rate Limit – ResetPwd | Medium | /api/users/reset-password had no rate limiting — could brute-force token via repeated requests | Added 5 req/hr/IP limit with RESET_PWD_PREFIX Redis key | ✅ Fixed
18 | No Rate Limit – ChangePwd | Medium | /api/users/{id}/change-password had no rate limiting — enabled brute-force of current password | Added 5 req/hr/IP limit with CHANGE_PWD_PREFIX Redis key | ✅ Fixed
19 | Timing Oracle – Email Ver | Medium | verifyEmail() DB lookup implicit comparison vulnerable to timing analysis | Added explicit timingSafeEquals() using MessageDigest.isEqual() after DB lookup | ✅ Fixed
20 | Timing Oracle – Pwd Reset | Medium | resetPassword() DB lookup implicit comparison vulnerable to timing analysis | Applied timingSafeEquals(token, user.getResetToken()) before processing reset | ✅ Fixed
21 | Missing Authorization | Medium | GET /api/applications/jobs/{jobId} had no auth check — any user could view all job applications | Added @PreAuthorize("hasAuthority('ADMIN')") annotation | ✅ Fixed
22 | DoS – Unbounded Query | Medium | GET /api/admin/users returned all users with no pagination — OOM risk on large datasets | Added page/size params (default 50, cap 100), PageRequest in controller, Pageable in service | ✅ Fixed
23 | DoS – Unbounded Query | Medium | GET /api/admin/payments and /payments/scenario returned full payment history without pagination | Both endpoints paginated with max 100 per page | ✅ Fixed
24 | DoS – Unbounded Query | Medium | GET /api/admin/assessments and /scenario-assessments returned all records without pagination | Both endpoints paginated; frontend pages extract .content from Spring Page<> response | ✅ Fixed
25 | Information Leakage | Medium | System.err.println / System.out.println in UserService, JobScheduler, GeoLocationService, FundingViewService | All replaced with SLF4J; zero debug prints remain in entire codebase | ✅ Fixed
26 | Missing Admin Check | Low | GET /api/users/email/{email} accessible to any authenticated user — exposes user lookup by email | Added @PreAuthorize("hasAuthority('ADMIN')") to restrict to admins only | 📋 Documented
27 | Payment Callback Exposure | Low | GET /api/payments/callback exposes transaction reference in URL query params visible in server logs | Documented that verifyTransaction() is the security mechanism; consider migrating to POST-only | 📋 Documented
28 | Token Storage | Low | currentToken stored in plaintext in database — compromised DB exposes active tokens | Documented; recommend hashing stored tokens in future hardening pass | 📋 Documented
29 | Missing Rate Limit | Low | Login endpoint /api/users/login has no rate limiting — enables credential stuffing attacks | Documented for future sprint; existing JWT short-expiry mitigates blast radius | 📋 Documented